## Sheet1
item | estimated hours | baseline due date | due date | status | notes
establish database |  | 2025-05-25 | 2025-05-25 | done
create algorithms for metrics done |  | 2025-05-27 | 2025-05-28 | done
create live metrics on running shift screen |  | 2025-05-27 | 2025-05-28 | done
create end shift screen | 3 | 2025-05-29 | 2025-05-29
create a final shift data table | 3 | 2025-05-29
machine uptime = avaliable time | 0.12 | 2025-05-29
create history page | 5 | 2025-05-30
tighten up shift logic, poka yoke | 5 | 2025-06-02
make an api for HQ | 2 | 2025-06-02
Alex analysis | 2 | 2025-06-03
release reva |  | 2025-06-04